PROJECT CHECKLIST

Culex pipiens Complex Pangenome

Snakemake Pipeline – Task Tracker

Tyler Maire and Collaborators

University of Maryland Global Campus

March 2026

Instructions: Print this document or use it digitally. Check off each task as completed. Each phase must be complete before downstream phases can run.

# Phase 0: Project Setup (Week 1)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| Repository and Environment |  |  |  |
| ☐ | Create GitHub repository (culex-pangenome) | GitHub repo URL | Tyler |
| ☐ | Set up directory structure (workflow/rules/, workflow/envs/, workflow/scripts/, config/, results/, resources/) | Directory tree | Tyler |
| ☐ | Write .gitignore (exclude results/, resources/, *.fasta, *.zip) | .gitignore | Tyler |
| ☐ | Write config/config.yaml with all parameters and accessions | config.yaml | Tyler |
| ☐ | Write config/samples.tsv with 5 rows (4 ingroup + outgroup) | samples.tsv | Tyler |
| ☐ | Write master Snakefile with all include statements and rule all | Snakefile | Tyler |
| ☐ | Install Snakemake and Mamba (conda install -c bioconda snakemake mamba) | snakemake --version works | All |
| ☐ | Verify dry run passes: snakemake -n --use-conda | No errors | Tyler |
| Team Onboarding |  |  |  |
| ☐ | All team members clone repository | Local copies | All |
| ☐ | All team members complete Snakemake tutorial (2 hrs) | Self-report | All |
| ☐ | Assign rule file ownership (A: download/qc/annot/repeats, B: orthology/functional, C: phylo/families, D: synteny/figures) | Ownership doc | Tyler |
| ☐ | Set up branch protection on main (require PR review) | GitHub settings | Tyler |

# Phase 1: Data Acquisition and QC (Weeks 1–3)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| download.smk |  |  |  |
| ☐ | Write workflow/envs/datasets.yaml (ncbi-datasets-cli) | datasets.yaml | A |
| ☐ | Write download_genome rule in download.smk | download.smk | A |
| ☐ | Download Cx. quinquefasciatus (GCF_015732765.1) | resources/genomes/Cx_quinquefasciatus.fasta | A |
| ☐ | Download Cx. pallens (GCF_016801865.2) | resources/genomes/Cx_pallens.fasta | A |
| ☐ | Download Cx. molestus (GCA_024516115.1) | resources/genomes/Cx_molestus.fasta | A |
| ☐ | Download Cx. pipiens (GCA_963924435.1) | resources/genomes/Cx_pipiens.fasta | A |
| ☐ | Download Cx. tarsalis outgroup (GCA_016859205.1) | resources/genomes/Cx_tarsalis.fasta | A |
| ☐ | Verify all 5 FASTA files are non-empty and chromosome-scale | Manual check | A |
| qc.smk |  |  |  |
| ☐ | Write workflow/envs/busco.yaml | busco.yaml | A |
| ☐ | Write workflow/envs/quast.yaml | quast.yaml | A |
| ☐ | Write busco rule (genome mode, diptera_odb10) | qc.smk | A |
| ☐ | Write quast rule (all genomes combined) | qc.smk | A |
| ☐ | Run BUSCO on all 5 genomes | results/busco/{sample}/ | A |
| ☐ | Run QUAST comparison | results/quast/ | A |
| ☐ | Verify all BUSCO scores >90% complete | Check report | A |
| ☐ | Record assembly stats in lab notebook (N50, size, scaffolds, GC%) | Lab notebook entry | A |

# Phase 2: Annotation Standardization (Weeks 2–4)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| annotation.smk |  |  |  |
| ☐ | Write workflow/envs/liftoff.yaml | liftoff.yaml | A |
| ☐ | Write workflow/envs/gffread.yaml | gffread.yaml | A |
| ☐ | Write liftoff rule (transfer Cx. quin. annotation to others) | annotation.smk | A |
| ☐ | Write copy_ref_annotation rule (Cx. quin. keeps original GFF3) | annotation.smk | A |
| ☐ | Write extract_proteins rule (gffread -y) | annotation.smk | A |
| ☐ | Write busco_proteins rule (protein mode) | annotation.smk | A |
| ☐ | Run Liftoff: Cx. quin. → Cx. pallens | results/annotation/Cx_pallens_liftoff.gff3 | A |
| ☐ | Run Liftoff: Cx. quin. → Cx. molestus | results/annotation/Cx_molestus_liftoff.gff3 | A |
| ☐ | Run Liftoff: Cx. quin. → Cx. pipiens | results/annotation/Cx_pipiens_liftoff.gff3 | A |
| ☐ | Run Liftoff: Cx. quin. → Cx. tarsalis (outgroup) | results/annotation/Cx_tarsalis_liftoff.gff3 | A |
| ☐ | Check Liftoff transfer rates (all >85%?) | unmapped_features.txt | A |
| ☐ | If <85%: switch to BRAKER3 de novo annotation (fallback plan) | Decision logged | A/Tyler |
| ☐ | Extract proteins for all 5 genomes | results/proteins/{sample}.fa | A |
| ☐ | Run BUSCO protein mode on all 5 proteomes | results/busco_proteins/ | A |
| ☐ | Verify protein BUSCO scores >85% complete | Check report | A |

# Phase 3: Ortholog Inference and Pangenome (Weeks 4–6)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| orthology.smk |  |  |  |
| ☐ | Write workflow/envs/orthofinder.yaml | orthofinder.yaml | B |
| ☐ | Write setup_orthofinder_input rule (copy proteins to input dir) | orthology.smk | B |
| ☐ | Write orthofinder rule | orthology.smk | B |
| ☐ | Run OrthoFinder (expect 2–8 hours depending on hardware) | results/orthofinder/output/ | B |
| ☐ | Verify Orthogroups.GeneCount.tsv exists and has all 5 species | Manual check | B |
| Pangenome Partitioning |  |  |  |
| ☐ | Write workflow/scripts/partition_pangenome.py | partition_pangenome.py | B |
| ☐ | Write partition_pangenome rule in orthology.smk | orthology.smk | B |
| ☐ | Run partitioning (core/shell/cloud/singletons for 4 ingroup forms) | partitioned_orthogroups.tsv | B |
| ☐ | Record pangenome summary (N core, N shell, N cloud, N singletons) | pangenome_summary.tsv | B |
| ☐ | Sanity check: core should be the majority of orthogroups | Manual check | B |

# Phase 4: Functional Annotation and Enrichment (Weeks 5–7)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| functional.smk |  |  |  |
| ☐ | Write workflow/envs/eggnog.yaml | eggnog.yaml | B |
| ☐ | Download eggNOG database (~44 GB, one-time) | resources/eggnog_data/ | B |
| ☐ | Write eggnog_mapper rule | functional.smk | B |
| ☐ | Run eggNOG-mapper on all 5 proteomes | results/eggnog/{sample}.emapper.annotations | B |
| ☐ | Write workflow/scripts/go_enrichment.R | go_enrichment.R | B |
| ☐ | Write go_enrichment rule | functional.smk | B |
| ☐ | Run GO enrichment (core vs. shell vs. cloud) | go_enrichment_results.tsv | B |
| Key Gene Family Counts |  |  |  |
| ☐ | Write workflow/scripts/tabulate_key_families.py | tabulate_key_families.py | B |
| ☐ | Tabulate P450, GST, CCE, OR, GR, IR, OBP, CSP, immune genes per form | key_family_counts.tsv | B |
| ☐ | Flag any families with major copy number differences between forms | Lab notebook entry | B |

# Phase 5: Phylogenomics (Weeks 4–7)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| phylogenomics.smk |  |  |  |
| ☐ | Write workflow/envs/mafft.yaml, trimal.yaml, iqtree.yaml, astral.yaml | 4 env files | C |
| ☐ | Write workflow/scripts/extract_sco.py (extract single-copy orthologs) | extract_sco.py | C |
| ☐ | Write align_sco rule (MAFFT --auto) | phylogenomics.smk | C |
| ☐ | Write trim_alignment rule (trimAl -automated1) | phylogenomics.smk | C |
| ☐ | Write workflow/scripts/concatenate_alignments.py | concatenate_alignments.py | C |
| ☐ | Write concatenate_alignments rule | phylogenomics.smk | C |
| ☐ | Write iqtree_concat rule (MFP + 1000 UFBoot) | phylogenomics.smk | C |
| ☐ | Write gene_trees rule (per-gene IQ-TREE) | phylogenomics.smk | C |
| ☐ | Write astral rule (coalescent species tree) | phylogenomics.smk | C |
| ☐ | Write concordance_factors rule (IQ-TREE --gcf --scf) | phylogenomics.smk | C |
| ☐ | Run full phylogenomics pipeline | concat_tree.treefile + astral.nwk + concord.cf.tree | C |
| ☐ | Verify tree topology is reasonable (outgroup roots correctly) | Manual check | C |
| ☐ | Record where Cx. pallens falls (with pipiens or quinquefasciatus?) | Lab notebook entry | C |
| ☐ | Record concordance factors (high or low for pallens branch?) | Lab notebook entry | C |

# Phase 6: Gene Family Evolution (Weeks 6–9)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| gene_families.smk |  |  |  |
| ☐ | Write workflow/envs/cafe.yaml | cafe.yaml | C |
| ☐ | Write workflow/scripts/format_cafe_input.py (filter families, ultrametric tree) | format_cafe_input.py | C |
| ☐ | Write prepare_cafe_input rule | gene_families.smk | C |
| ☐ | Write cafe5 rule | gene_families.smk | C |
| ☐ | Write workflow/scripts/parse_cafe.py (extract significant families) | parse_cafe.py | C |
| ☐ | Write parse_cafe_results rule | gene_families.smk | C |
| ☐ | Run CAFE5 | results/cafe/output/ | C |
| ☐ | Identify families with p < 0.05 on specific branches | significant_families.tsv | C |
| ☐ | Cross-reference significant families with eggNOG annotations | Lab notebook entry | C |
| Positive Selection (Optional but Recommended) |  |  |  |
| ☐ | Write workflow/envs/paml.yaml | paml.yaml | C |
| ☐ | Select top 10–20 candidate families for PAML branch-site test | Candidate list | C |
| ☐ | Run PAML codeml on candidate families | PAML results per family | C |
| ☐ | Record any genes under positive selection | Lab notebook entry | C |

# Phase 7: Synteny and Structural Variation (Weeks 5–8)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| synteny.smk |  |  |  |
| ☐ | Write workflow/envs/minimap2.yaml (minimap2 + samtools) | minimap2.yaml | D |
| ☐ | Write workflow/envs/syri.yaml (syri + plotsr) | syri.yaml | D |
| ☐ | Write workflow/envs/mummer.yaml | mummer.yaml | D |
| ☐ | Write minimap2_align rule (all 6 pairwise comparisons) | synteny.smk | D |
| ☐ | Write syri rule | synteny.smk | D |
| ☐ | Write plotsr rule | synteny.smk | D |
| ☐ | Write nucmer_dotplot rule | synteny.smk | D |
| ☐ | Run all 6 pairwise alignments | results/synteny/*.bam | D |
| ☐ | Run SyRI on all 6 pairs | results/synteny/*_syri.out | D |
| ☐ | Generate plotsr synteny figure | results/figures/synteny_plot.pdf | D |
| ☐ | Generate all 6 nucmer dotplots | results/figures/dotplot_*.png | D |
| Chromosome 3 Inversion Analysis |  |  |  |
| ☐ | Write workflow/scripts/check_3Rb_inversion.py | check_3Rb_inversion.py | D |
| ☐ | Parse SyRI output for chr3 inversions specifically | 3Rb_status_report.tsv | D |
| ☐ | Determine if 3Rb is shared across forms or unique to quinquefasciatus | Lab notebook entry | D |

# Phase 8: Transposable Element Analysis (Weeks 7–10)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| repeats.smk |  |  |  |
| ☐ | Write workflow/envs/repeatmasker.yaml (RepeatModeler + RepeatMasker) | repeatmasker.yaml | A |
| ☐ | Write repeatmodeler rule (build de novo library from Cx. quin.) | repeats.smk | A |
| ☐ | Write repeatmasker rule (mask all 4 ingroup genomes with same library) | repeats.smk | A |
| ☐ | Run RepeatModeler (~12–24 hrs) | custom_repeat_lib.fa | A |
| ☐ | Run RepeatMasker on all 4 ingroup genomes | results/repeats/{sample}/ | A |
| ☐ | Write workflow/scripts/plot_te_landscape.R (Kimura divergence plots) | plot_te_landscape.R | A |
| ☐ | Write te_landscape rule | repeats.smk | A |
| ☐ | Generate TE landscape comparison figure | te_landscape_comparison.pdf | A |
| ☐ | Record % genome masked per TE class per species | Lab notebook entry | A |
| TE-Gene Proximity (Optional) |  |  |  |
| ☐ | Write workflow/scripts/te_gene_proximity.py | te_gene_proximity.py | A |
| ☐ | Compare TE proximity for core vs. accessory genes | te_proximity_results.tsv | A |

# Phase 9: Publication Figures (Weeks 8–12)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| figures.smk – All 8 Manuscript Figures |  |  |  |
| ☐ | Fig 1: Assembly overview (BUSCO bars + QUAST stats + ideograms) | fig1_assembly_overview.pdf | A |
| ☐ | Fig 2a: UpSet plot (orthogroup sharing intersections) | fig2a_upset.pdf | B |
| ☐ | Fig 2b: Flower/petal diagram (core center, form-specific petals) | fig2b_flower.pdf | B |
| ☐ | Fig 2c: Pangenome accumulation curve | fig2c_accumulation.pdf | B |
| ☐ | Fig 3: Species tree with bootstrap + concordance factors | fig3_species_tree.pdf | C |
| ☐ | Fig 4: CAFE5 gene family evolution on tree branches | fig4_gene_family_evolution.pdf | C |
| ☐ | Fig 5: Whole-genome synteny (plotsr multi-panel) | synteny_plot.pdf | D |
| ☐ | Fig 6: GO enrichment heatmap (core vs. shell vs. cloud) | go_enrichment_heatmap.pdf | B |
| ☐ | Fig 7: Key gene family copy number comparison | fig7_key_families.pdf | B |
| ☐ | Fig 8: TE landscape Kimura divergence plots | te_landscape_comparison.pdf | A |
| Figure Quality Checks |  |  |  |
| ☐ | All figures use consistent color palette across panels | Visual check | Tyler |
| ☐ | All figures have readable axis labels at print size | Visual check | Tyler |
| ☐ | All figures exported as PDF (vector) at 300+ DPI | File check | Tyler |
| ☐ | Species names italicized in all figure labels | Visual check | Tyler |

# Phase 10: Pipeline Validation and Documentation (Weeks 10–12)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| End-to-End Validation |  |  |  |
| ☐ | Clean run: delete results/ and rerun snakemake --use-conda --cores 8 | Full pipeline completes | Tyler |
| ☐ | Verify all expected output files exist | results/ tree check | Tyler |
| ☐ | Run snakemake --report report.html and review | report.html | Tyler |
| ☐ | Generate DAG: snakemake --dag ¦ dot -Tpng > dag.png | dag.png | Tyler |
| Documentation |  |  |  |
| ☐ | Write comprehensive README.md (overview, installation, usage, citation) | README.md | Tyler |
| ☐ | Document all config.yaml parameters with comments | config.yaml updated | Tyler |
| ☐ | Add LICENSE file (MIT or GPL-3.0) | LICENSE | Tyler |
| ☐ | Add CHANGELOG.md | CHANGELOG.md | Tyler |
| Archiving |  |  |  |
| ☐ | Push final pipeline to public GitHub repository | Public repo | Tyler |
| ☐ | Create Zenodo DOI for pipeline release (v1.0.0) | Zenodo DOI | Tyler |
| ☐ | Add Zenodo badge to README.md | README updated | Tyler |

# Phase 11: Manuscript Writing (Weeks 12–18)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| Drafting |  |  |  |
| ☐ | Write Introduction (background, gap, rationale, objectives) | Intro draft | Tyler |
| ☐ | Write Methods: Data acquisition and QC | Methods §2.1 | A |
| ☐ | Write Methods: Annotation standardization | Methods §2.2 | A |
| ☐ | Write Methods: Ortholog inference and pangenome partitioning | Methods §2.3 | B |
| ☐ | Write Methods: Functional annotation and enrichment | Methods §2.4 | B |
| ☐ | Write Methods: Phylogenomics | Methods §2.5 | C |
| ☐ | Write Methods: Gene family evolution and selection | Methods §2.6 | C |
| ☐ | Write Methods: Synteny and structural variation | Methods §2.7 | D |
| ☐ | Write Methods: Transposable element analysis | Methods §2.8 | A |
| ☐ | Write Methods: Snakemake pipeline and reproducibility | Methods §2.9 | Tyler |
| ☐ | Write Results: Assembly comparison | Results §3.1 | A |
| ☐ | Write Results: Pangenome composition | Results §3.2 | B |
| ☐ | Write Results: Functional enrichment | Results §3.3 | B |
| ☐ | Write Results: Species tree and concordance | Results §3.4 | C |
| ☐ | Write Results: Gene family evolution | Results §3.5 | C |
| ☐ | Write Results: Synteny and structural variants | Results §3.6 | D |
| ☐ | Write Results: TE landscapes | Results §3.7 | A |
| ☐ | Write Discussion | Discussion draft | Tyler |
| ☐ | Write Abstract (last, after all sections complete) | Abstract | Tyler |
| Revision and Polish |  |  |  |
| ☐ | All co-authors review complete draft | Comments collected | All |
| ☐ | Tyler integrates feedback and revises | Revised draft | Tyler |
| ☐ | Format for GBE (check author guidelines) | Formatted manuscript | Tyler |
| ☐ | Prepare supplementary materials (pipeline DOI, supp. tables, supp. figs) | Supp. files | All |
| ☐ | Write cover letter | Cover letter | Tyler |

# Phase 12: Submission (Weeks 18–22)

| ✓ | Task | Output / Deliverable | Owner |
| --- | --- | --- | --- |
| Pre-Submission Checklist |  |  |  |
| ☐ | All figures embedded at correct resolution | File check | Tyler |
| ☐ | All accession numbers verified in manuscript | Text check | Tyler |
| ☐ | Pipeline GitHub URL and Zenodo DOI included in Data Availability | Text check | Tyler |
| ☐ | All author names, affiliations, and ORCIDs correct | Text check | All |
| ☐ | Reference list complete and formatted for CSE name-year (GBE style) | Text check | Tyler |
| ☐ | Conflict of interest statement prepared | Text | Tyler |
| Submission |  |  |  |
| ☐ | Submit to GBE via ScholarOne | Confirmation email | Tyler |
| ☐ | If rejected: revise and submit to BMC Genomics (backup) | Resubmission | Tyler |
| Post-Submission |  |  |  |
| ☐ | Respond to reviewer comments (if revisions requested) | Revised manuscript | All |
| ☐ | Post preprint to bioRxiv (optional, discuss with team) | bioRxiv DOI | Tyler |

# Quick Reference: Who Owns What

| Person | Rule Files | Manuscript Sections |
| --- | --- | --- |
| Person A | download.smk, qc.smk, annotation.smk, repeats.smk | Methods 2.1–2.2, 2.8; Results 3.1, 3.7 |
| Person B | orthology.smk, functional.smk | Methods 2.3–2.4; Results 3.2–3.3 |
| Person C | phylogenomics.smk, gene_families.smk | Methods 2.5–2.6; Results 3.4–3.5 |
| Person D | synteny.smk, figures.smk (coordination) | Methods 2.7; Results 3.6 |
| Tyler | Snakefile, config, README, repo management | Introduction, Discussion, Abstract, Methods 2.9 |